## Sprint i
| User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a customer, I want to be able to have easy access to pleasing color palettes for when I am stuck and can’t come up with any myself. | Make a layout for how the palettes will look | 1 | Basics of the website are done. | F | 5 | 0
7 | As a customer, I want a clean and seamless browsing experience, so I can enjoy using the website without distractions. | Ensure website is polished and looks good |  |  | F | 1 | 1 | Everyone
10 | As a customer, I want to be able to create a palette based on a specific color so I can have a similar feel throughout the whole build. | Write an average color of png algorithm. |  |  | F | 3 | 3 | Owen leavitt 50%, Addam Shover 50%
|  | Store Minecraft textures somewhere |  |  |  | 2 | 2 | Will Dolley 100%
23 |  | Make all documentation (product backlog, sprint backlog, project description, sprint review, SRS, kanban) |  |  | F | 4 | 4 | Everyone
23 | Make user stories | Create and finish user stories document |  |  | F | 4 | 4 | Everyone
18 | As a customer, I want an easy to use circle generator tool so I can create circular designs and layouts for my projects, so that I can efficiently create circular designs and layouts for my projects. | Make circle generator working | 2 | Make circle generator working | F | 2 | 2 | Kenny 75%, Kylie 25%
23 |  | Make all documentation (product backlog, sprint backlog, project description, sprint review, SRS, kanban) |  |  | F | 4 | 4 | Everyone
3 | As a customer, I want to see palettes based on the blocks I already know I want to use, so that the palettes more accurately fit my vision for what I want the build to look like. | Create a filter for the block generator which will create palettes with the required blocks its given . | 3 | Make a functional log in. | F | 0 | 1
17 | As a customer, I want to be able to submit multiple criteria, so I can receive customized color palettes, so I can create my design/build with the exact colorway I need and want. | Make the color generator have multiple filters. |  |  | F | 4 | 4 | Addam 50%, Owen 50%
21 | As a customer, I want to be able to log in for increased functionality | Create a log in page that will allow for users to save their color palettes. |  |  | F | 1 | 3
23 |  | Make all documentation (product backlog, sprint backlog, project description, sprint review, SRS, kanban) | 3 |  | F | 4 | 4 | everyone
24 |  | QC documents | 3 |  | NT | 2 | 2 | everyone
6 | As a customer, I want to be able to save block palettes that I like, so I can easily reference them later. | Make a function tha t will allow for users to save pallets and view them later | 4 | Find a way to save palletes | f | 1 | 0 | everyone
19 | As a customer, I want to be able to sort by blocks that are non-flammable, so that I can easily identify safe materials for building projects that require fire resistance. | Create an option that will allow users to toggle a non-flamable generator |  | Create flamable tags to the blocks | f | 2 | 2 | Addam 100%
23 |  | Make all documentation + revisions | 4 |  | NT | 3 | 3 | everyone
24 |  | Set up CI and tests | 4 |  | NT | 2 | 2 | Will 100%
26 |  | QC documents | 4 |  | NT | 2 | 2 | everyone
20 | As a customer, I want to be able to see what other people like, so I can get inspiration for my designs from looking at theirs. | Make a universal pallete observer , where everyone can upload and see other peoples pallets | 5 | make a public server for pallets | f | 5 | 0
5 | As a customer, I want to be able to share my palettes with others, so I can collaborate with teammates or clients. | Create a public server where multiple people can veiw and edit color palletts |  | Create editable and viewable pallets | f | 2 | 1 | Addam 50%, Owen 50%
23 |  | Make all documentation + revisions | 5 |  | NT | 4 | 3 | Will 25%, Addam 25%, Owen 25%, Kenny 25%
24 |  | Update tests + make more | 5 |  | NT | 3 | 3 | Owen 33% , Addam 33%, Will 33%
26 |  | QC documents | 5 |  | NT | 2 | 0.5 | Didnt really get done
25 |  | Polish Website | 6 | Finishing touches, make sure everything is ready | NT | 1 | 1 | Owen 30%, Addam 60%, Kenny 10%
25 |  | Make slideshow/video | 6 |  | NT | 3 | 3 | Will 100%
23 |  | Make all documentation + revisions | 6 |  | NT | 4 | 4 | Will 75%, Owen 25%
24 |  | Make new tests | 6 |  | NT | 2 | 1 | Owen 100%
22 | As a customer, I want a way to easily acquire these blocks in game | Make new feature (acquisition of blocks) | 6 |  | F | 2 | 2 | Addam 75%, Owen 25%
26 |  | QC documents | 6 |  | NT | 2 | 2 | Owen 75%, Will 25%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657